## Scoring matrix
Age discrimination remedy risk assessment
Objectives:
1. Immediate Detriment: Members entitled to payment of legacy scheme benefits before 2022-2023
2. Prospective remedy: Move all members to FPS 2015 at 1 April 2022
3. Deferred choice underpin (DCU) – part 1: All members reverted to legacy scheme for remedy period
4. DCU – part 2: Maintenance of underpinned CARE records frpm 1 April 2015 to DOL
5. DCU – part 3: Choice given at crystallisation
Scope:
Joint stakeholder risk register to reflect interdepenencies between parties in the implementation of age discrimination remedy
Related resources:
LGA project implementation document [LINK]
Likelihood of Risk Occurring
| Rare (1) |  |  |  | Unlikely (2) |  |  | Possible (3) |  |  | Likely (4) | Almost certain (5)
| Less than a 5% chance of circumstances arising OR Has happened rarely / never |  |  |  | 5% to 20% chance of circumstances arising OR Only likely to happen once every 3 or more years |  |  | 20% to 40% chance of circumstances arising OR Likely to happen in the next 2 to 3 years OR Risk seldom encountered |  |  | 40% to 70% chance of circumstances arising OR Likely to happen at some point in the next 1 to 2 years OR Risk occasionally encountered | 70% to 100% chance of circumstances arising OR Likely to happen at some point in the next 12 months OR Risk frequently encountered
Impact if Risk Occurs
| Insignifcant (1) |  |  |  | Minor (2) |  |  | Moderate (3) |  |  | Major (4) | Extreme (5)
| Minimal or no effect on the achievement of objectives AND / OR Minimal or no effect on the delivery of objectives - Very confident the risk can be improved AND / OR Very achievable objective Very easily influenced Very tolerable / easy to accept - Insignificant reputational damage AND / OR No media attention |  |  |  | Little effect on the achievement of objectives AND / OR Little effect of the delivery of objectives - Confident the risk can be improved AND / OR Achievable objective Easily influenced Tolerable/ acceptable - Minimal damage to reputation (minimal negative coverage in press or social media) |  |  | Partial failure to achieve objectives AND / OR Partial failure to deliver objectives - Moderately confident that the risk can be improved AND / OR Possible to achieve objective Able to influence Somewhat tolerable - Some reputational damage/ loss of confidence AND / OR Some negative coverage in press/ social media |  |  | Significant impact on achieving objectives AND / OR Significant impact on delivering objectives - Little confidence the risk can be improved AND / OR Unlikely to achieve objective Difficult to influence Out of tolerance but possible to accept - Significant reputational damage/ loss of confidence AND /OR Significant press coverage / significant social media attention | Catastrophic impact on achieving objectives AND / OR Catastophic impact on delivering objectives - Almost certain risk cannot be improved AND / OR Unachievable objective Impossible to influence Out of tolerance/ acceptance - Extensive reputational damage (including press coverage)
|  |  | Risk Matrix | [5 empty] | Risk Score
| IMPACT | 5 Extreme | 5 | 10 | 15 | 20 | 25 |  | Risk Score | Tier Rating
|  | 4 Major | 4 | 8 | 12 | 16 | 20 |  | 1 - 5 | T1
|  | 3 Moderate | 3 | 6 | 9 | 12 | 15 |  | 6 - 14 | T2
|  | 2 Minor | 2 | 4 | 6 | 8 | 10 |  | 15 - 25 | T3
|  | 1 Insignificant | 1 | 2 | 3 | 4 | 5
|  |  | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost certain
LIKELIHOOD

## Risk heat map
Age discrimination remedy risk heat map
|  | Risk Matrix at DATE | [7 empty] | Risk Score
| 5 Extreme | [8 empty] | Risk Score |  | RAG Rating
| 4 Major |  |  | 4. 7 | 1. 8. 13 | 12 |  |  |  | 1 - 5 |  | T1
IMPACT | 3 Moderate |  | 10 | 5. 6. 9. 11 | 3 | 2 |  |  |  | 6 - 14 |  | T2
| 2 Minor | [8 empty] | 15 - 25 |  | T3
1 Insignificant
|  | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost certain
LIKELIHOOD
| Risk # |  |  | Date | Change | Date | Change | Date | Change | Date | Change
No Change è | 1 | Timeframes for policy development - Primary (HMT) - Secondary (Home Office) |  | Score |  | Score |  | Score |  | Score
Decreasing ê | 2 | Knowingly working without legislation, policy, and software development (i.e. immediate detriment before 1 April 2022-2023) |  | Score |  | Score |  | Score |  | Score
Increasingé | 3 | Potential for continuing to work without legislation due to delays, legal challenges etc. |  | Score |  | Score |  | Score |  | Score
| 4 | Unknown HMT expectations on delivery (for example legislation dates, further development of tax policy and guidance) |  | Score |  | Score |  | Score |  | Score
| 5 | Mutual dependencies of stakeholder landscape |  | Score |  | Score |  | Score |  | Score
| 6 | Technical complexity of scheme regulations. Interaction with overriding legislation. |  | Score |  | Score |  | Score |  | Score
| 7 | Ineffective contract management of administrators or software suppliers by FRAs and administrators. |  | Score |  | Score |  | Score |  | Score
| 8 | Scheme administration and management complexity |  | Score |  | Score |  | Score |  | Score
| 9 | Judicial review challenges to the proposed new legislation. Legal challenges to the processes in place to implement remedy. |  | Score |  | Score |  | Score |  | Score
| 10 | Lack of engagement from key stakeholders |  | Score |  | Score |  | Score |  | Score
| 11 | Ineffective governance and monitoring |  | Score |  | Score |  | Score |  | Score
| 12 | Insufficient resources |  | Score |  | Score |  | Score |  | Score
| 13 | Inaccurate or incomplete data |  | Score |  | Score |  | Score |  | Score

## Risk and mitigation register
Age discrimination remedy risk and mitigation register
|  |  |  | CURRENT |  |  |  |  | TARGET
| Risk Type (b) | Owner (c) | Risk Name / Description (d) | Likelihood (e) | Impact (f) | Risk Score (g) | Impact / Consequences (h) | Controls (i) | Likelihood (j) | imp score | Impact (k) | Like score | Risk Score (l) | Mitigations (m) | Owner (n) | Next Review (q)
1 | Regulatory/ Legislative | Home Office LGA Scheme managers Admin | Timeframes for policy development - Primary (HMT) - Secondary (Home Office) | 4 | 4 | 16 | Primary policy sets timeframes for everything that follows. Any delay will have knock-on effect e.g. late engagement with sector stakeholders. Limited resources at Home Office and GLD due to conflicting pressures i.e. Brexit and COVID-19 and Matthews. Therefore a shorter timeframe for secondary policy development could lead to drafting errors. | LGA attendance at HMT working groups to understand and represent challenges to sector inc. on timescales. Regular and open engagement between HO and LGA. Framework created in advance of policy decisions being known to act quickly once these are communicated (e.g. senior stakeholder group, SAWG). | 3 |  | 3 |  | 9 | Early identification of potential areas of challenge and conflicting time pressures (i.e. Matthews). LGA offer to proof read draft regulations. | LGA Home Office | At each meeting
2 | Regulatory/ Legislative | Scheme managers Admin | Knowingly working without legislation, policy, and software development (i.e. immediate detriment before 1 April 2022-2023) | 5 | 3 | 15 | Risk of acting ultra-vires. Increase in manual calculations means more resource required and greater scope for error. Incorrect calculation of benefits leading to over/ underpayments and complaints from members. Duplication of workload due to revisiting past cases. | LGA information note and matrix. Opportunity to relay challenges directly to HMT and Home Office. Early discussions with software providers | 4 | 5 | 2 | 5 | 8 | Revision of HO informal guidance. Wording for waiver to be provided by HMT. Scheme managers to have clear decision making processes in place. Administrators to develop robust procedures for processing and recording cases. Stakeholders to ensure appropriate resources in place to deal with increased workloads. | LGA Home Office Scheme managers Admin | At each meeting
3 | Regulatory/ Legislative | LGA Scheme managers Admin | Potential for continuing to work without legislation due to delays, legal challenges etc. | 4 | 3 | 12 | Subsequent delays to development of software and automated processes. Increase in manual calculations means more resource required and greater scope for error. Incorrect calculation of benefits leading to over/ underpayments and complaints from members. Duplication of workload due to revisiting past cases. | Early identification of potential areas of challenge. Opportunity to relay challenges directly to HMT and Home Office. | 4 | 5 | 3 | 5 | 12 | Scheme managers to have clear decision making processes in place. Administrators to develop robust procedures for processing and recording cases. Stakeholders to ensure appropriate resources in place to deal with increased workloads. | Scheme managers Admin | At each meeting
4 | Regulatory/ Legislative | LGA Scheme managers Admin | Unknown HMT expectations on delivery (for example legislation dates, further development of tax policy and guidance) | 3 | 4 | 12 | Uncertainty over timescales for different elements of delivery (e.g. primary, secondary, statutory guidance, and if this will be retrospective). Difficulty developing communication and implementation strategies. Impact on resource planning and budgeting. | LGA attendance at HMT working groups to understand and represent challenges to sector inc. on timescales. Regular and open engagement between HO and LGA. Framework created in advance of policy decisions being known to act quickly once these are communicated (e.g. senior stakeholder group, SAWG). Maintenance of LGA project implementation document to allow internal resources to be most effectively directed. | 3 | 5 | 3 | 5 | 9 |  | LGA Home Office Scheme managers Admin | At each meeting
5 | Operational | LGA Scheme managers Admin SAB LPBs | Mutual dependencies of stakeholder landscape | 3 | 3 | 9 | Stakeholders working in isolation and to differing timescales. Inconsistent communication and implementation. Leading to different outcomes for members and potential for future legal challenge. | An understanding by stakeholders of their responsibilities and inter-dependencies. Peer working with NPCC to identify dependencies and opportunities for collaboration between Fire and Police schemes. Regular reporting to senior stakeholder group Agreement of parties to project leadership by LGA pensions team. | 2 | 5 | 2 | 5 | 4 | LGA to provide opportunity for training and networking events to share knowledge and best practice. Engagement of senior management at FRAs through NFCC network. Participation in working groups to be facilitated by the LGA (e.g. software suppliers, SAWG, technical and communications). Establish software development needs and expectations. LGA to support sector to consider provision of FPS management and admin services and development of improved procurement routes. Encourage development and adoption of standard products and approaches, such as online tools and national communications. | All parties | At each meeting
6 | Compliance | Home Office LGA Scheme managers Admin | Technical complexity of scheme regulations. Interaction with overriding legislation. | 3 | 3 | 9 | Challenge of interpreting and applying complex regulations and understanding how these interact with overriding legislation e.g. tax. Delivery of Matthews remedy will mean further SI amendments and increased complexity. Lack of clarity over interaction of Sargeant with Matthews e.g. eligibility. Potential for incorrect application, leading to member complaints (IDRP) and breaches of law. Increase in TPO determinations and reputational damage. | Existing LGA support offer including technical support, frameworks for regional/ national groups, and FPS regs website. Supportive engagement from HO on technical queries/ interpretation of policy intent. | 2 | 5 | 3 | 5 | 6 | LGA to explore options for provision of external resources such as: - legal advice - tax advice - tax training and support Ensure sector has access to knowledge and information about the changes being made, via website and bulletins. LGA to seek and promote consistent interpretations of scheme rules. | LGA | At each meeting
7 | Operational | Scheme managers Admin | Ineffective contract management of administrators or software suppliers by FRAs and administrators. | 3 | 4 | 12 | Late delivery of solutions or software not fit for purpose as specifications not clearly defined. Associated risks of working without systems in place. Being overcharged for services due to last minute procurement or SLAs too vague i.e key components not included within core costs. | Scheme managers to have clear decision making processes in place. Periodic review of suppliers undertaken. | 2 | 5 | 2 | 5 | 4 | LGA to support sector to consider provision of FPS management and admin services and development of improved procurement routes. LGA to provide governance training to allow Local Pension Boards to successfully scrutinise and monitor local delivery. | LGA Scheme managers Admin | At each meeting
8 | Operational | Scheme managers Admin | Scheme administration and management complexity | 4 | 4 | 16 | FPS widely acknowledged to be complex to manage and administer, in part due to structure i.e. 45 FRAs across 18 admin. Increasing number of administrators withdrawing from FPS market. Assoc. risks from lack of procurement routes. Delivery of Matthews remedy will further increase complexity of running schemes. Potential for incorrect application of scheme regulations, leading to member complaints (IDRP) and breaches of law. Increase in TPO determinations and reputational damage. | Scheme managers to have clear decision making processes in place. Survey of FRAs to assess current arrangements and preparedness for remedy (Sargeant and Matthews). | 3 | 5 | 3 | 5 | 9 | LGA to support sector to consider provision of FPS management and admin services and development of improved procurement routes. LGA to provide governance training to allow Local Pension Boards to successfully scrutinise and monitor local delivery. Stakeholders to ensure appropriate resources in place to deal with increased workloads. | LGA Scheme managers Admin | At each meeting
9 | Regulatory/ Legislative | LGA Scheme managers Admin | Judicial review challenges to the proposed new legislation. Legal challenges to the processes in place to implement remedy. | 3 | 3 | 9 | Ongoing litigation could lead to delay in legislation being laid and implementation of remedy. Increased uncertainty of timescales to employers and employees. Additional cost pressure on FRAs in defending cases. | Working closely with LGA workforce colleagues to keep informed of any legal developments. Framework created in advance of policy decisions being known to act quickly once these are communicated (e.g. senior stakeholder group, SAWG). | 3 | 5 | 3 | 5 | 9 | Early identification of potential areas of challenge. Opportunity to relay challenges directly to HMT and Home Office. | LGA Home Office | At each meeting
10 | Operational | LGA Scheme managers Admin | Lack of engagement from key stakeholders | 2 | 3 | 6 | Failure to implement remedy effectively. Potential for incorrect application of scheme regulations, leading to member complaints (IDRP) and breaches of law. Increase in TPO determinations and reputational damage. | An understanding by stakeholders of their responsibilities and inter-dependencies. Agreement of parties to project leadership by LGA pensions team. Oversight and transparency of project provided by SAB, as part of their scrutiny and governance role. | 2 | 5 | 2 | 5 | 4 | LGA to provide opportunity for training and networking events to share knowledge and best practice. Participation in working groups to be facilitated by the LGA. Engagement of senior management at FRAs through NFCC network. | LGA Scheme managers Admin | At each meeting
11 | Compliance | LGA SAB Scheme managers Local Pension Boards | Ineffective governance and monitoring | 3 | 3 | 9 | Failure to implement remedy effectively. TPR engagement/ intervention. Increase in TPO determinations and reputational damage. | Oversight and transparency of project provided by SAB, as part of their scrutiny and governance role. | 2 | 5 | 2 | 5 | 4 | Ensure that stakeholders are made aware of additional or existing responsibilities as a result of age discrimination, so that FRAs have the information necessary to make decisions. Scheme managers to have clear decision making processes in place. Provide governance training to allow Local Pension Boards to successfully scrutinise and monitor local delivery of remedy. | LGA SAB Scheme managers Local Pension Boards | At each meeting
12 | Operational | All parties | Insufficient resources to implement Sargeant remedy in addition to business as usual. Potential for concurrent implementation of Matthews. | 5 | 4 | 20 | Limited resources at Home Office and GLD due to conflicting pressures i.e. Brexit, COVID-19 and Matthews could lead to drafting errors in legislation. Failure of LGA to deliver project deliverables. Failure to implement remedy effectively. Potential for incorrect application of scheme regulations, leading to member complaints (IDRP) and breaches of law. TPR engagement/ intervention. Increase in TPO determinations and reputational damage. | Agreement of parties to project leadership by LGA pensions team. Maintenance of LGA project implementation document to allow internal resources to be most effectively directed. Opportunity to relay challenges directly to HMT and Home Office. Peer working with NPCC to identify dependencies and opportunities for collaboration between Fire and Police schemes. Survey of FRAs to assess current arrangements and preparedness for remedy. | 4 | 5 | 3 | 5 | 12 | Sector to look at opportunities for collaboration to avoid duplication and save time/ resources. Budgeting/ recruiting for additional resource where necessary and appropriate. | All parties | At each meeting
13 | Operational | Scheme managers Admin | Inaccurate or incomplete data | 4 | 4 | 16 | Lack of accurate member records or inability to collect required data leading to failure to implement remedy effectively. Subsequent member complaints (IDRP) and breaches of law. TPR engagement/ intervention. Increase in TPO determinations and reputational damage. | FRAs to work closely with administrators to identify gaps. FRAs to robustly evidence where data cannot be obtained/ retrieved. | 3 | 5 | 2 | 5 | 6 | Provision of data collection guidance and standard template (LGA). Potential to agree standard assumptions with sector. Establish software development needs and expectations for creation and maintenance of additional data fields. | LGA Scheme managers Admin | At each meeting